## Main-approved
| GENERAL FUND CAPITAL PROGRAMME - ESTIMATED EXPENDITURE 2023-24 to 2028-29 |  |  |  | Revised budget baseline | Actual exp | Forecast
2023-24
| Directorate/Service and Capital Scheme name | Approved gross estimate | Cumulative spend at 31-03-23 | Estimate approved by Council in February | Revised estimate | Expenditure at 02.01.24 | Projected exp est by project officer | 2024-25 Est for year | 2025-26 Est for year | 2026-27 Est for year | 2027-28 Est for year | 2028-29 Est for year | 2029-30 Est for year | 2030-31Est for year | 2031-32 Est for year | Future years est exp | Projected expenditure total | Grants / Contributions towards cost of scheme | Funded from Reserves | Net cost of scheme | Total net cost approved by Executive | Variance between projected expenditure to approved estimate | Variance between total cost to Council to approved estimate
|  | (a) | (b) | (c) | (d) | (e) | (f) | (ii) | (iii) | (iv) | (v) | (v) | (v) | (v) | (i) | (g) | (b)+(f)+(g) = (h) | (i) | (j) | (h)-(i) -(j)= (k) | (k) | (g)-(j) = (l) | (i)-(k) = (m)
|  | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 |  | £000 | £000 | £000 | £000
APPROVED SCHEMES
COMMUNITY WELLBEING DIRECTORATE
General Fund Housing
| Disabled Facilities Grants |  | annual | 605 | 605 | 357.4598 | 605 | 605 | 0 | 0 | 0 |  |  |  |  | 605 | 1210 | -1210 | 0 | 0
| Better Care Fund |  | annual | 0 | 0 | 266.3254 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
| Home Improvement Assistance |  | annual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | - | 0 | 0
| Solar Energy Loans |  | annual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | - | 0 | 0
| BCF TESH Project |  | annual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
| BCF Prevention grant |  | annual | 0 | 0 | 8.5093 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0
| SHIP |  | annual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | - | 0 | 0
| General Grants to HAs |  | annual | 100 | 100 | 0 | 100 | 100 | 0 | 0 | 0 |  |  |  |  | 100 | 200 | - | 0 | 200
| COMMUNITY WELLBEING DIRECTORATE TOTAL | 0 | 0 | 705 | 705 | 632.2946 | 705 | 705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 705 | 1410 | -1210 | 0 | 200 | 0 | 0 | 0
PLACE DIRECTORATE
| Assets and Property |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | - | 0 | 0
| Methane gas monitoring system | 100 | 48.019 | 52 | 51.981 | 0 | -0.019 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 100 | - | 0 | 100 | 100
| Energy efficiency compliance - Council owned properties | 245 | 101.711 | 133 | 143.289 | 0 | 0.289 | 143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143 | 245 | - | 0 | 245 | 25 | 0 | 220
| Bridges -Inspections and remedial works | 317 | 256.45 | 0 | 60.55 | 14.7907 | 60.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317 | - | 0 | 317 | 67 | 0 | 250
| Tyting Farm Land-removal of barns and concrete hardstanding | 200 | 143.037 | 57 | 57 | 7.4529 | 10 | 47 | 0 | 0 | 0 |  |  |  |  | 47 | 200.037 | 0 | 0 | 200.037
| Flood resilience measures (use in conjunction with grant funded schemes) | 445 | 323.824 | 0 | 121.176 | 0 | 0.176 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121 | 445 | 0 |  | 445 | 124 | 0 | 321
| Merrow lane grille & headwall construction | 60 | 3.009 | 0 | 57 | 0 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 60.009 | 0 |  | 60.009 | 60
| PLACE DIRECTORATE TOTAL | 1367 | 876.05 | 242 | 490.996 | 22.2437 | 70.996 | 420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420 | 1367.046 | 0 | 0 | 1367.046 | 376 | 0 | 791
COMMUNITY WELLBEING DIRECTORATE
Community Services
| Traveller transit site provision | 127 |  | 0 | 127 | 0 | 0 | 127 | 0 | 0 | 0 | 0 |  |  |  | 127 | 127 | 0 |  | 127 |  |  | Executive 14 Jan 2019 20.06.19 moved £90k fRom 19-20 to 20-21 27.08.19 DA moved £72K too approved Bellfields Green 19.09.19 SA to check and adz 30.09.19 DA moved £48k to approved Shalford Common 09.06.20 DA moved £5k to approved spectrum 18.06.20 PS move £75k to 2122 23.06.20 as per CM approval 30.04.20 moved £4k to approved Bellfields 14.10.20 DA approved CM moved further £6k to Bellfields 18.03.21 moved £40k to 2122 as not reqd this fy
Environmental Services
| Vehicles, Plant & Equipment Replacement Programme | 12815 | 10529.384 | 149 | 136 | 30.002 | 70 | 2216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2216 | 12815.384 | -26 |  | 12789.384 | 2945 | annual | annual
| Crown court CCTV | 10 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 |  | 10 | 10
| Town Centre CCTV upgrade | 106 | 0 | 125 | 250 | 0 | 0 | 106 | 0 | 0 | 0 | 0 |  |  |  | 106 | 106 | -106 |  | 0 |  |  | Executive 14 Jan 2019 20.06.19 TP to liaise with GF and adz 19.09.19 TP to advise
| Redevelopment of Westborough and Park Barn play area | 376.494 | 0 | 320 | 376.494 | 90.9578 | 376.494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 376.494 | -56.494 |  | 320 | 625 | annual | annual
| Stoke cemetry re-tarmac | 122 | 77.097 | 0 | 45 | 0 | 45 | 0 | 0 | 0 | - | - | - | - | - | 0 | 122.097 | 0 |  | 122.097 | 47
| Parks and Countryside - repairs and renewal of paths,roads and car parks | 355 | 336.864 | 0 | 18 | 18 | 18 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 354.864 | 0 |  | 354.864
| Shalford Common - regularising car parking/reduction of encroachments | 121 | 35.88 | 92 | 85 | 1.91 | 10 | 75 | 0 | 0 | 0 | 0 |  |  |  | 75 | 120.88 | 0 |  | 120.88
| Traveller encampments | 53 |  | 26 | 53 | 2.96 | 3 | 50 | 0 | 0 | 0 | 0 |  |  |  | 50 | 53 | 0 |  | 53
| Stoke Park Paddling Pool (complete) | 170 | 168.269 | 0 | 2 | 2 | 2 | 0 | [7 empty] | 0 | 170.269 |  |  | 170.269
| Lido - Drainage Works and Changing Rooms | 2100 | 1168.152 | 200 | 879 | 730.2465 | 879 | 53 | 0 | [6 empty] | 53 | 2100.152 |  | -1500 | 600.152
| SMP astro turf surface (complete) | 3 |  | 8 | 8 | 2.95 | 3 | 0 | 0 | [6 empty] | 0 | 3 |  |  | 3
| Crematorium Bollards & Lampost | 5 |  |  | 5 | 0 | 5 | 0 | 0 | [6 empty] | 0 | 5 |  |  | 5
| Derby Road playground conversion | 120 |  | 120 | 30 | 0 | 30 | 0 | [7 empty] | 0 | 30 |  |  | 30
| COMMUNITY WELLBEING TOTAL DIRECTORATE | 16483.494 | 12315.646 | 1040 | 2024.494 | 879.0263 | 1441.494 | 2637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2637 | 16394.14 | -188.494 | -1500 | 14705.646 | 3627 | 0 | 0
TRANSFORMATION & GOVERNANCE DIRECTORATE
0
Finance
| Capital contingency fund | annual | - | 2000 | 1820 | 0 | 1820 | 2000 | 2000 | 2000 | 2000 | 0 | 2000 | 2000 | 0 | 8000 | 9820 | - |  | 9820 | 5000
| TRANSFORMATION & GOVERNANCE DIRECTORATE TOTAL | 0 | 0 | 2000 | 1820 | 0 | 1820 | 2000 | 2000 | 2000 | 2000 | 0 | 2000 | 2000 | 0 | 8000 | 9820 | 0 |  | 9820 | 5000 | 0 | 0
DEVELOPMENT/INCOME GENERATING/COST REDUCTION PROJECTS
Development / Infrastructure PLACE DIRECTORATE
| Rodboro Buildings - electric theatre through road and parking | 416 | 39.031 | 379 | 377 | 0.45512 | 0 | 377 | 0 | 0 | 0 | 0 |  |  |  | 377 | 416.031 | 0 |  | 416.031
| Walnut Bridge replacement | 5097.514 | 5641.981 | 0 | 0 | 39.6414 | 39.6414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5681.6224 | -2459.687 | -950.38 | 2271.5554 | -2271.5554
| SMC(West) Phase 1 (complete) | 1944 | 1927.576 | 0 | 39 | 15.5381 | 16 | 0 | 0 | [6 empty] | 0 | 1943.576 | -914.396 |  | 1029.18
| Ash Road Bridge | 44000 | 9189.205 | 22491 | 30473 | 7648.3085 | 19349 | 14966 | 496 | 0 | 0 | 0 | 0 | 0 | 0 | 15462 | 44000.205 | -35965.3742 |  | 8034.8308
| Ash Road Footbridge | 500 | 182.688 | 36 | 317 | 0.0792 | 0 | 317 | 0 | 0 | 0 | 0 |  |  |  | 317 | 499.688 | 0 | 0 | 499.688 |  |  | 30.09.19 Exec 24 Sep added to programme to be funded £2.5m Network Rail and other contributions to be agreed 18.06.20 LF/Cf moved £4.4m to 2122 as planning in Jan 29.03.21 EXEC 26 Mar 2021 addtl est of £221k approved amended funding as only £2.5m from Network Rail updated cashflow profile as per exec rpt
| Broadband for Surrey Hills (B4SH) | 60 | 46.275 | 0 | 14 | 0.995 | 1 | 13 | [7 empty] | 13 | 60.275 |  |  | 60.275
| Guildford West (PB) station (moved to Capital Vision) | 500 | 0 | 250 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | - | 0 | 0 | 0 |  | 0 | 100
Development Financial - PLACE DIRECTORATE
| Middleton Ind Est Redevelopment | 15007 | 12859.618 | 300 | 2147 | 2022.6858 | 2147 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 15006.618 |  |  | 15006.618
| Property acquisitions | 12697 | 9675.459 | 23953 | 23845 | 1630.096 | 2022 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 12697.459 | 0 |  | 12697.459 | 100
| Rebuild Crematorium(complete) | 11111 | 10933.855 | 0 | 177.145 | 176.813 | 177.145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11111 | 0 |  | 11111 | 500 | 0 | 10611
| North Street Development / Guild Town Centre regeneration | 1727 | 1585.888 | 100 | 141 | 56.5525 | 141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1726.888 | -250 |  | 1476.888 | 899
| Shaping Guildford Future (SGF) (no longer reqd) | 4170 |  | 2640 | 4170 | 0 | 0 | 0 | [7 empty] | 0 | 0 |  |  | 0
| Internal Estate Road - CLLR Phase 1 | 11139 | 10945.538 | 0 | 193.462 | 896.1466 | 193.462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11139 | -5106.7668 |  | 6032.2332 | 500 | 0 | 5532.2332
P | WUV (Weyside Urban Village) | 170506 | 29004.059 | 93223 | 110452 | 5653.3927 | 43943 | 66509 | 0 |  | 0 | 0 | 0 | 0 | 0 | 66509 | 170705.876 | -56787.489 |  | 113918.387 | 384 | 199.876 | 113534.387
| WUV - Allotment relocation | 200 | 3441.85 | 0 | 0 | 281.3107 | 0 | 0
| WUV - Int roads, Site clearance | 0 | 0.552 | 0 | 0 | 1144.5213 | 0
| WUV - New GBC Depot | 2480 | 2423.7 | 0 | 56.3 | 577.9038 | 56.3 | 0 | [7 empty] | 0 | 2480 |  |  | 2480
| WUV - Off Site Highways |  |  | 0 | 0 | 529.6101 | 0 | 0 | [7 empty] | 0
| WUV - Thames Water relocation | 0 | 26716.825 | 0 | 0 | 17075.3405 | 0
| WUV -Utilities & Plot services |  |  | 0 | 0 | 77.4854 | 0 | 0 | [7 empty] | 0 | 0 |  |  | 0
| WUV - Land Purchase | 0 | 1090.59 | 0 | 0 | 0 | 0
| WUV - Waste Transfer Centre |  |  |  |  | 0.07563
| WUV - Commercial Development |  |  |  |  | 0.07563
| WUV - SANG |  |  | 0 | 0 | 212.0268 | 0 | 0 | [7 empty] | 0 | 0 |  |  | 0
| WUV - Common Land |  |  | 0 | 0 | 113.3903 | 0 | 0 | [7 empty] | 0 | 0 |  |  | 0
| DEVELOPMENT/INCOME GENERATING/COST REDUCTION PROJECTS TOTAL | 281554.514 | 125704.69 | 143372 | 172901.907 | 38152.4443 | 68085.5484 | 83182 | 496 | 0 | 0 | 0 | 0 | 0 | 0 | 83678 | 277468.2384 | -101483.7131 | -950.38 | 175034.1453 | 2383 | 199.876 | 129677.6202
| APPROVED SCHEMES TOTAL | 299405.008 | 138896.386 | 147359 | 177942.397 | 39686.0089 | 72123.0384 | 88944 | 2496 | 2000 | 2000 | 0 | 2000 | 2000 | 0 | 95440 | 306459.4244 | -102882.2071 | -2450.38 | 201126.8373 | 11386 | 199.876 | 130468.6202
| non-development projects total | 17850.494 | 13191.696 | 3987 | 5040.49 | 1533.5646 | 4037.49 | 5762 | 2000 | 2000 | 2000 | 0 | 2000 | 2000 | 0 | 11762 | 28991.186 | -1398.494 | -1500 | 26092.692 | 9003 | 0 | 791
| development/infrastructure - non-financial benefit | 52517.514 | 17026.756 | 23156 | 31720 | 7705.0174 | 19405.6414 | 15673 | 496 | 0 | 0 | 0 | 0 | 0 | 0 | 16169 | 52601.3974 | -39339.4572 | -950.38 | 12311.5601
| development- financial benefit | 229037 | 108677.934 | 120216 | 141181.907 | 30447.4269 | 48679.907 | 67509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67509 | 224866.841 | -62144.2558 | 0 | 162722.5852 | 2383 | 199.876 | 129677.6202
| TOTAL | 299405.008 | 138896.386 | 147359 | 177942.397 | 39686.0089 | 72123.0384 | 88944 | 2496 | 2000 | 2000 | 0 | 2000 | 2000 | 0 | 95440 | 306459.4244 | -102882.2071 | -2450.38 | 201126.8373 | 11386 | 199.876 | 130468.6202
SUMMARY
| APPROVED SCHEMES - TOTAL | 299405.008 | 138896.386 | 147359 | 177942.397 | 39686.0089 | 72123.0384 | 88944 | 2496 | 2000 | 2000 | 0 | 2000 | 2000 | 0 | 95440 | 306459.4244 | -102882.2071 |  | 201126.8373 | 11386 | 199.876 | 130468.6202
| GRAND TOTAL | 299405.008 | 138896.386 | 147359 | 177942.397 | 39686.0089 | 72123.0384 | 88944 | 2496 | 2000 | 2000 | 0 | 2000 | 2000 | 0 | 95440 | 306459.4244 | -102882.2071 |  | 201126.8373 | 11386 | 199.876 | 130468.6202
Note on E6: worsfoldv: as per Executive report in January
Note on V29: worsfoldv: £57k saving identified
Note on V78: worsfoldv: 28/5 - increased from £218k to £234k as part of budget report Jan 12

## Main-prov
GENERAL FUND CAPITAL PROGRAMME - ESTIMATED EXPENDITURE 2023-24 to 2028-29
2022-23
| Directorate / Service Units Capital Schemes | Gross estimate approved by Executive | Cumulative spend at 31-03-23 | Estimate approved by Council in February | Revised estimate | Expenditure at 02.01.24 | Projected exp est by project officer | 2024-25 Est for year | 2025-26 Est for year | 2026-27 Est for year | 2027-28 Est for year | 2028-29 Est for year | 2029-30 Est for year | 2030-31Est for year | 2031-32 est for yr and SARP to 3233 | Future years estimated expenditure | Projected expenditure total |  | Grants or Contributions towards cost of scheme | Net total cost of scheme to the Council | Total net cost approved by Executive | Variance between projected expenditure to approved estimate | Variance between total cost to Council to approved estimate
|  | (a) | (b) | (c) | (e) | (f) | (g) | (i) | (ii) | (iii) | (iv) | (v) | (v) | (v) | (v) | (h) | (b)+(g)+(h)=(i) |  | (j) | (i) - (j) = (k) | (l) | (g)-(j) = (l) | (i)-(k) = (m)
|  | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 |  | £000 | £000 | £000 | £000 | £000
PROVISIONAL SCHEMES (schemes approved in principle; further report to the Executive required)
PLACE DIRECTORATE
Assets and Property
| Methane gas monitoring system | 150 | 0 | 150 | 150 | 0 | 0 | 150 | 0 | 0 |  | 0 | 0 | 0 | 0 | 150 | 150 |  | - | 150 | 200
| Energy efficiency compliance - Council owned properties & Energy & CO2 reduction in Council non HRA properties | 3218 | 0 | 2718 | 2718 | 0 | 0 | 0 | 2718 | 500 |  | 0 | 0 | 0 | 0 | 3218 | 3218 |  | - | 3218 | 1150
| Bridges | 370 | 0 | 0 | 370 | 0 | 0 | 370 | 0 | 0 |  | 0 | 0 | 0 | 0 | 370 | 370 |  | - | 370 | 570
| Investment Property void pot | 500 |  | 100 | 100 | 0 | 100 | 100 | 100 | 100 | 100 | 0 |  |  |  | 400 | 500 |  |  | 500
| Surface water management plan | 200 | 0 | 200 | 200 | 0 | 0 | 200 | 0 | 0 | 0 | 0 |  | 0 | 0 | 200 | 200 |  | 0 | 200 | 200
| Chilworth Gunpowder Mills | 180 |  | 165 | 175 | 0 | 20 | 160 | 0 | [6 empty] | 160 | 180 |  |  | 180
| PLACE DIRECTORATE TOTAL | 4618 | 0 | 3333 | 3713 | 0 | 120 | 980 | 2818 | 600 | 100 | 0 | 0 | 0 | 0 | 4498 | 4618 |  | 0 | 4618 | 2120 | 0 | 0
COMMUNITY WELLBEING DIRECTORATE
Environmental Services
| Vehicles, Plant & Equipment Replacement Programme | 21850 | 0 | 2900 | 2900 | 0 | 0 | 0 | 3085 | 2766 | 7183 | 5330 | 2000 | 600 | 886 | 21850 | 21850 |  | 0 | 21850 | 4591 | annual | annual
| Refurbishment / rebuild Sutherland Memorial Park Pavilion (no longer reqd) | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 100 | annual | annual
| Stoke Pk gardens water feature refurb (no longer reqd) | 40 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | - | - | 0 | 0 |  | -29.0662 | -29.0662 | 100
| Parks and Countryside - repairs and renewal of paths,roads and car parks | 1382 | 0 | 250 | 250 | 0 | 0 | 500 | 250 | 250 | 382 | 0 |  |  |  | 1382 | 1382 |  | 0 | 1382
| Millmead fish pass | 60 | 0 | 0 | 60 | 0 | 0 | 60 | 0 | 0 | 0 | 0 |  |  |  | 60 | 60 |  | 0 | 60
| Memorial Wall | 100 |  | 0 | 0 | 0 | 0 | 0 | 100 | 0 | [5 empty] | 100 | 100 |  |  | 100
| Stoke cemetry re-tarmac | 18 |  | 0 | 18 | 0 | 18 | 0 | [7 empty] | 0 | 18 |  |  | 18
| Lido Road Allotment Security Fencing | 70 |  | 70 | 70 | 0 | 70 | 0 | [7 empty] | 0 | 70 |  |  | 70
| 2015 Play strategy action plan (no longer reqd) | 200 |  | 200 | 200 | 0 | 0 | 0 | [7 empty] | 0 | 0 |  |  | 0
| COMMUNITY WELLBEING DIRECTORATE TOTAL | 23870 | 0 | 3460 | 3538 | 0 | 88 | 560 | 3435 | 3016 | 7565 | 5330 | 2000 | 600 | 886 | 23392 | 23480 | 0 | -29.0662 | 23450.9338 | 4791 | 0 | 0
TRANSFORMATION & GOVERNANCE DIRECTORATE
Commercial Services
| Spectrum upgrades | 7100 |  | 1250 | 1250 | 0 | 0 | 3000 | 2300 | 1150 | 650 | 0 |  |  |  | 7100 | 7100 |  |  | 7100
| TRANSFORMATION & GOVERNANCE DIRECTORATE TOTAL | 7100 | 0 | 1250 | 1250 | 0 | 0 | 3000 | 2300 | 1150 | 650 | 0 | 0 | 0 | 0 | 7100 | 7100 | 0 | 0 | 7100 | 0 | 0 | 0
DEVELOPMENT/INCOME GENERATING/COST REDUCTION PROJECTS
Development / Infrastructure - PLACE DIRECTORATE
| Investment in North Downs Housing (no longer reqd) | 30100 | 0 | 5518 | 5518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  | - | 0
| Equity shares in Guildford Holdings ltd (no longer reqd) | 0 | 0 | 3683 | 3683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  | - | 0
| Sustainable Movement Corrider (no longer reqd) | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | - | - | - | 0 | 0 |  | 0 | 0 | 100
| Guildford West (PB) station (moved to Capital Vision) | 1000 | 0 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 |  | 0 | - | - | - | 0 | 0 |  | 0 | 0 | 100
| Westfield/Moorfield rd resurfacing | 3152 | 0 | 0 | 0 | 0 | 0 | 3152 | 0 | 0 | 0 | 0 | - | - | - | 3152 | 3152 |  | 0 | 3152 | 100
Development Financial - PLACE DIRECTORATE
| GBC Depot - operational | 2430 |  | 200 | 200 | 0 | 200 | 2200 | 30 | 0 | [5 empty] | 2230 | 2430 |  |  | 2430
P | WUV (Weyside Urban Village) | 150622 | 0 | 1522 | 1522 | 0 | 0 | 83450 | 51057 | 10025 | 0 | 0 | 0 | 0 | 0 | 144532 | 144532 |  | 0 | 144532 | 104680 | -6090 | 39852
| North Street development | 1250 | 0 | 50 | 50 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 950 | 0 | 0 | 1200 | 1250 |  | 0 | 1250 | 21134 | 0 | -19884
| Property acquisitions (no longer reqd) | 38291.55 | 0 | 28292 | 28292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 100
| DEVELOPMENT/INCOME GENERATING/COST REDUCTION PROJECTS TOTAL | 226995.55 | 0 | 40265 | 40265 | 0 | 250 | 88852 | 51137 | 10075 | 50 | 50 | 950 | 0 | 0 | 151114 | 151364 | 0 | 0 | 151364 | 126214 | -6090 | 19968
| PROVISIONAL SCHEMES - GRAND TOTALS | 262583.55 | 0 | 48308 | 48766 | 0 | 458 | 93392 | 59690 | 14841 | 8365 | 5380 | 2950 | 600 | 886 | 186104 | 186562 | 0 | -29.0662 | 186532.9338 | 133125 | -6090 | 19968
| non development projects | 35588 | 0 | 8043 | 8501 | 0 | 208 | 4540 | 8553 | 4766 | 8315 | 5330 | 2000 | 600 | 886 | 34990 | 35198 | 0 | -29.0662 | 35168.9338
| development/infrastructure - non-financial benefit | 34402 | 0 | 10201 | 10201 | 0 | 0 | 3152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3152 | 3152 | 0 | 0 | 3152
| development- financial benefit | 192593.55 | 0 | 30064 | 30064 | 0 | 250 | 85700 | 51137 | 10075 | 50 | 50 | 950 | 0 | 0 | 147962 | 148212 | 0 | 0 | 148212 | 125914 | -6090 | 19968
| TOTAL | 262583.55 | 0 | 48308 | 48766 | 0 | 458 | 93392 | 59690 | 14841 | 8365 | 5380 | 2950 | 600 | 886 | 186104 | 186562 | 0 | -29.0662 | 186532.9338 | 125914 | -6090 | 19968
SUMMARY
| PROVISIONAL SCHEMES - TOTAL | 262583.55 | 0 | 48308 | 48766 | 0 | 458 | 93392 | 59690 | 14841 | 8365 | 5380 | 2950 | 600 | 886 | 186104 | 186562 |  | -29.0662 | 186532.9338 | 133125 | -6090 | 19968
| GRAND TOTAL | 262583.55 | 0 | 48308 | 48766 | 0 | 458 | 93392 | 59690 | 14841 | 8365 | 5380 | 2950 | 600 | 886 | 186104 | 186562 |  | -29.0662 | 186532.9338 | 133125 | -6090 | 19968
Note on E6: worsfoldv: as per Executive report in January

## Reserve
GENERAL FUND CAPITAL SCHEMES - PROJECTS FUNDED VIA RESERVES: ESTIMATED EXPENDITURE 2023-24 to 2028-29 APPENDIX 7
2022-23
Projects & Sources of Funding | #REF! | Approved gross estimate | Cumulative spend at 31-03-23 | Estimate approved by Council in February | Revised estimate | Expenditure at 02.01.24 | Projected exp est by project officer | 2024-25 Est for year | 2025-26 Est for year | 2026-27 Est for year | 2027-28 Est for year | 2028-29 Est for year | Future years est exp | Projected expenditure total
|  | (a) | (b) | (c) |  | (e) | (f) | (i) | (ii) | (iii) | (iv) | (v) | (g) | (b)+(f)+(g) = (h)
|  | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
PLACE DIRECTORATE
ENERGY PROJECTS per SALIX RESERVE:(PR220) |  |  |  | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 0
LED lighting |  | 44 |  | 0 | 44 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 44
ENERGY PROJECTS per GBC INVEST TO SAVE RESERVE:
GBC 'Invest to Save' energy projects (to be repaid in line with savings) |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0
SMP - air source heat pump |  | 28 | 0.68 | 0 | 27.32 | 0 | 27.32 | 0 | 0 | 0 | 0 | 0 | 0 | 28
ENERGY RESERVES TOTAL |  | 72 | 0.68 | 0 | 71.32 | 0 | 71.32 | 0 | 0 | 0 | 0 | 0 | 0 | 72
CAR PARKS RESERVE
Car parks - install/replace pay-on-foot equipment |  | 1170 | 240.061 | 0 | 0 | 0 | 0 | 930 | 0 | 0 | 0 | 0 | 930 | 1170.061
Lift replacement (PR000293) |  | 841 | 715.904 | 0 | 125.096 | 0 | 125.096 | 0 | 0 | 0 | 0 | 0 | 0 | 841
Structural works to MSCP |  | 300 | 50 | 0 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 150
Additional barriers Farnham Rd |  | 15 |  | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 15
Deck surface replacement (stair cores)Farnham Rd |  | 70 |  | 0 | 70 | 5.3148 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 70
Structural repairs roof turret timbers Castle St Car Park |  | 210 |  | 200 | 200 | 0 | 20 | 190 | 0 | 0 | 0 | 0 | 190 | 210
CAR PARKS RESERVE TOTAL |  | 2606 | 1005.965 | 200 | 510.096 | 5.3148 | 330.096 | 1120 | 0 | 0 | 0 | 0 | 1120 | 2456.061
COMMUNITY WELLBEING DIRECTORATE
INFORMATION TECHNOLOGY - IT Renewals Reserve (PR265) : approved annually
Hardware / software budget |  | 500 |  | 440 | 440 | 0 | 440 | 0 | 0 |  | 0 | 0 | 0 | 440
Hardware |  | annual | annual | 0 | 0 | 72.6382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software |  | annual | annual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ICT Refresh Phase 2 |  |  |  | 60 | 60 | 5.71 | 60 | 0 | 0 |  |  | 0 | 0 | 60
Salesforce |  | 1200 | 195.697 |  |  | 130.5602 | 130.5602
IDOX Acolaid to Uniform |  | 275 |  | 275 | 275 |  | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 275
LCTS alternative |  | 56.375 |  | 56 | 56.375 |  | 56.375 | 0 |  | 0 | 0 | 0 | 0 | 56.375
IT RENEWALS RESERVE TOTAL |  | 2031.375 | 195.697 | 831 | 831.375 | 208.9085 | 961.9352 | 0 | 0 | 0 | 0 | 0 | 0 | 831.375
SPA RESERVE :
SPA schemes (various) |  | 100 | annual | 0 | 151 | 0 | 151 | 0 | 0 | 0 | 0 | 0 | 0 | 151
Chantry Woods | [5 empty] | 0 | 0 | [5 empty] | 0
Effingham | [5 empty] | 0 | 0 | [5 empty] | 0
Lakeside | [5 empty] | 0 | 0 | [5 empty] | 0
Riverside | [5 empty] | 0 | 0 | [5 empty] | 0
Parsonage | [5 empty] | 0 | 0 | [5 empty] | 0
SPA RESERVE TOTAL |  | 100 | 0 | 0 | 151 | 0 | 151 | 0 | 0 | 0 | 0 | 0 | 0 | 151
TRANSFORMATION & GOVERNANCE DIRECTORATE
SPECTRUM RESERVE
Spectrum schemes (to be agreed with Freedom Leisure) |  | 431 | 168 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 168
SPECTRUM RESERVE TOTAL |  | 431 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168
GRAND TOTALS |  | 5240.375 | 1370.342 | 1031 | 1563.791 | 214.2233 | 1514.3512 | 1120 | 0 | 0 | 0 | 0 | 1120 | 3678.436

## S106
GENERAL FUND CAPITAL PROGRAMME - S106 ESTIMATED EXPENDITURE 2023-24 to 2028-29
|  |  |  | Target/Actual Dates | [7 empty] | 2022-23
Useful Life of asset (yrs) | Residual value of asset | Asset classification | Asset ref / CC | Contract sign | Start on site | Finish on site | Ret'n | Code | Service Units / Capital Schemes | Approved gross estimate | Cumulative spend at 31-03-23 | Estimate approved by Council in February | Revised estimate | Expenditure at 02.01.24 | Projected exp est by project officer | 2024-25 Est for year | 2025-26 Est for year | 2026-27 Est for year | 2027-28 Est for year | 2028-29 Est for year | Future years est exp | Projected expenditure total | Grants / Contributions towards cost of scheme | Net cost of scheme | Variance between projected expenditure to approved estimate | Variance between total cost to Council to approved estimate
[10 empty] | (a) | (b) | (c) | (d) | (e) | (f) | (i) | (ii) | (iii) | (iv) | (v) | (g) | (b)+(f)+(g) = (h) | (i) | (h)-(i) | (g)-(j) = (l) | (i)-(k) = (m)
[10 empty] | £000 | £000 | £000 |  | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
APPROVED SCHEMES (fully funded from S106 contributions)
COMMUNITY WELLBEING DIRECTORATE
Environmental Services
[8 empty] | P18177 | Gunpowder mills - signage, access and woodland imps | 36 | 21.632 | 14 | 14.368 | 1.3052 | 14.368 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | -36 | 0
[8 empty] | P18192 | Chantry Wood Campsite | 36 |  | 36 | 36 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | -36 | 0
[8 empty] | P18225 | Foxenden Quarry | 100.728 | 54.177 | 59 | 47 | 17.8552 | 47 | 0 |  |  |  |  | 0 | 101.177 | -101.177
[8 empty] | P18230 | Boardwalk Heathfield Nature Reserve | 13.244 |  | 13 | 13 | 0 | 13 | 0 |  |  |  |  | 0 | 13 | -13.244
[8 empty] | P18241 | Shalford park Trim Trail | 11.661 |  |  | 12 |  | 12 | 0 |  |  |  |  | 0 | 12 | -12
[8 empty] | P18242 | GLIVE Landscaping | 1.174 |  |  | 1.174 | 1.1741 | 1.174 | [6 empty] | 1.174 | -1.174
[8 empty] | P18243 | The Briars Playarea | 169 |  |  | 169 |  | 169 | [6 empty] | 169 | -169
[8 empty] | P18245 | Stoke Park Fencing of Feature Planting & Ponw | 10.036 |  |  | 10.036 | 10.0357 | 10.036 | [6 empty] | 10.036 | -10.036
[9 empty] | COMMUNITY WELLBEING DIRECTORATE TOTAL | 377.843 | 75.809 | 122 | 302.578 | 30.3701 | 302.578 | 0 | 0 | 0 | 0 | 0 | 0 | 378.387 | -377.631 | 0 | 0 | 0
[9 empty] | APPROVED S106 SCHEMES TOTAL | 377.843 | 75.809 | 122 | 302.578 | 30.3701 | 302.578 | 0 | 0 | 0 | 0 | 0 | 0 | 378.387 | -377.631 | 0 | #REF! | #REF!
Note on M6: worsfoldv: as per Executive report in January
Note on P6: worsfoldv: Spend to date plus remaining months profiled estimated spend

## Resources
GENERAL FUND CAPITAL PROGRAMME : SUMMARY OF RESOURCES AND FINANCIAL IMPLICATIONS
| 1.0 | AVAILABILITY OF RESOURCES - NOTES :
| 1.1 | The following balances have been calculated taking account of estimated expenditure on the approved capital schemes
| 1.2 | The actuals for 2022-23 have not been audited.
| 1.3 | Funding assumptions:
1. All capital expenditure will be funded in the first instance from available capital receipts and the General Fund capital programme reserve.
2. Once the above resources have been exhausted in any given year, the balance of expenditure will be financed from borrowing, both internally
and externally, depending upon the Council's financial situation at the time.
| 1.4 | These projections are based on estimated project costs, some of which will be 'firmed up' in due course. Any variations to the estimates
and the phasing of expenditure will affect year on year funding projections.
| 2.0 | Capital receipts - Balances (T01001) |  | 2022-23 | 2023-24 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29
|  |  |  | Actuals | Budget | Est Outturn | Estimate | Estimate | Estimate | Estimate | Estimate
|  |  |  | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
|  |  | Balance as at 1 April | 127.013 | 0 | 136.446 | 0 | 0 | 0 | 2813.947 | 7999.707
|  |  | Add estimated usable receipts in year | 168.593 | 0 | 2545 | 2000 | 39109.045 | 18904.947 | 15550.76 | 56227.08
|  |  | Less applied re funding of capital schemes | -159.16 | 0 | -2681.446 | -2000 | -39109.045 | -16091 | -10365 | -5380
| Balance after funding capital expenditure as at 31 March |  |  | 136.446 | 0 | 0 | 0 | 0 | 2813.947 | 7999.707 | 58846.787
during year = outturn (col v, actual = col u)
| 3.0 | Capital expenditure and funding - summary |  | 2022-23 | 2023-24 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29
|  |  |  | Actuals | Budget | Est Outturn | Estimate | Estimate | Estimate | Estimate | Estimate
|  |  |  | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
Estimated captial expenditure
|  |  | Main programme - approved | 34053.0916 | 147359 | 72123.0384 | 88944 | 2496 | 2000 | 2000 | 0
|  |  | Main programme - provisional | 0 | 48308 | 458 | 93392 | 59690 | 14841 | 8365 | 5380
|  |  | s106 | 282.7085 | 122 | 302.578 | 0 | 0 | 0 | 0 | 0
|  |  | Reserves | 1109.3443 | 1031 | 1514.3512 | 1120 | 0 | 0 | 0 | 0
|  |  | GF Housing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total estimated capital expenditure | 35445.1444 | 196820 | 74397.9676 | 183456 | 62186 | 16841 | 10365 | 5380
To be funded by:
|  |  | Capital receipts (per 2.above) | -159.16 | 0 | -2681.446 | -2000 | -39109.045 | -16091 | -10365 | -5380
|  |  | Contributions | -6861.785 | -46336 | -49078.936 | -20622 | -1020 | -750 | 0 | 0
R.C.C.O. :
|  |  | Other reserves | -2388.9152 | -1131 | -1797.6592 | -1192 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | -9409.8602 | -47467 | -53558.0413 | -23814 | -40129.045 | -16841 | -10365 | -5380
|  |  | Balance of funding to be met from (i) the Capital Reserve, and (ii) borrowing | -26035.2842 | -149353 | -20839.9264 | -159642 | -22056.955 | 0 | 0 | 0
|  |  | Total funding required | -35445.1444 | -196820 | -74397.9676 | -183456 | -62186 | -16841 | -10365 | -5380
| 4.0 | General Fund Capital Schemes Reserve (U01030) |  | 2022-23 | 2023-24 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29
|  |  |  | Actuals | Budget | Est Outturn | Estimate | Estimate | Estimate | Estimate | Estimate
|  |  |  | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
|  |  | Balance as at 1 April | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Add: | General Fund Revenue Budget variations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Contribution from revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Less: | Applied re funding of capital programme | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Balance after funding capital expenditure etc.as at 31 March | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Estimated shortfall at year-end to be funded from borrowing |  |  |  | 26035.2842 | 149353 | 20839.9264 | 159642 | 22056.955 | 0 | 0 | 0
| 5.0 | Housing capital receipts (pre 2013-14) - estimated |  | 2022-23 | 2023-24 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29
|  | availability/usage for Housing, Affordable Housing and |  | Actuals | Budget | Est Outturn | Estimate | Estimate | Estimate | Estimate | Estimate
|  | Regeneration projects - GBC policy |  | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
|  |  | Balance as at 1 April (T01008) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Add: | Estimated receipts in year | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Less: | Applied re Housing (General Fund) capital programme | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Less: | Applied re Housing company | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Equity in Hsg Co
|  | Less: | Applied re Housing Improvement programme
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Less: | Applied on regeneration schemes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Housing receipts - estimated balance in hand at year end |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5.1 | Housing capital receipts (post 2013-14) - estimated availability/usage |  | 2022-23 | 2023-24 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29
|  | availability/usage for Housing, Affordable Housing and |  | Actuals | Budget | Est Outturn | Estimate | Estimate | Estimate | Estimate | Estimate
|  | Regeneration projects only (statutory (impact CFR)) |  | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
|  |  | Balance as at 1 April (T01012) | 50.099 | 348 | 0 | 360 | 371 | 383 | 395 | 410
|  | Add: | Estimated receipts in year | 644.761 | 301 | 0 | 304 | 307 | 310 | 313 | 0
|  | Less: | Applied re Housing (General Fund) capital programme | 0 | -189 | 0 | -72 | -75 | -78 | -78 | 0
|  | Less: | Applied re Housing Improvement programme | -694.86 | -100 | 0 | -220 | -220 | -220 | -220 | -410
|  |  |  | 0 | 360 | 0 | 371 | 383 | 395 | 410 | 0
|  | Less: | Applied on regeneration schemes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Housing receipts - estimated balance in hand |  | 0 | 360 | 0 | 371 | 383 | 395 | 410 | 0
Total £'000s
| 6.1 | Estimated annual borrowing requirement |  | 26035.2842 | 149353 | 20839.9264 | 159642 | 22056.955 | 0 | 0 | 0 | 202538.8814
|  | Bids for funding (net) | [9 empty] | 0
|  | Total estimated borrowing requirement if all bids on Appendix 1 approved |  |  | 149353 | 20839.9264 | 159642 | 22056.955 | 0 | 0 | 0 | 202538.8814
0
0
0
0
0
[6 empty] | 0 | -9361
[7 empty] | reserves | reserves | reserves | reserves
-1000
|  |  | u/n to borrow - BB 17/18-21/2 plus r/over |  |  | 12412 | 0 | 0 | 0 | 0 | 0 | 12412
|  |  |  | 2028-29: 0 | 0
12412
|  |  | more reserves | [8 empty] | -3938
8474
202538.8814
-194064.8814
Note on E37: worsfoldv: Non reserve spend plus vehicles / borrowing spend
Note on E40: worsfoldv: from Capoutturn non reserve contr
Note on E43: worsfoldv: capoutturn financing statement - RCCO
Note on E44: worsfoldv: from financing statement capoutturn
Note on E56: Michele Rogers: need to verify once reserve jnl actioned
Note on E69: nuttg: needs to agree with figures in Hsg.cap. Prog. (GF element)
Note on E70: nuttg: needs to agree with figures in Hsg.cap. Prog. (GF element)
Note on E83: nuttg: needs to agree with figures in Hsg.cap. Prog. (GF element)
Note on E84: nuttg: needs to agree with figures in Hsg.cap. Prog. (GF element)
Note on F69: nuttg: needs to agree with figures in Hsg.cap. Prog. (GF element)
Note on F70: nuttg: needs to agree with figures in Hsg.cap. Prog. (GF element)
Note on F83: nuttg: needs to agree with figures in Hsg.cap. Prog. (GF element)
Note on F84: nuttg: needs to agree with figures in Hsg.cap. Prog. (GF element)
Note on G71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Adjusted formula - so no negative reserve!
Note on G83: nuttg: needs to agree with figures in Hsg.cap. Prog. (GF element)
Note on H40: worsfoldv: From table B estimates sheet (list of contr to offset exp in table A (est exp))
Note on H68: worsfoldv: T01008 & T01009
Note on H82: worsfoldv: T01008 & T01009
Note on H96: Michele Rogers: 1065 from approved not in budget in error
Note on I40: worsfoldv: From table B estimates sheet (list of contr to offset exp in table A (est exp))
Note on J40: worsfoldv: From table B estimates sheet (list of contr to offset exp in table A (est exp))
Note on J96: Michele Rogers: 220 not included in budget in error
Note on K40: worsfoldv: From table B estimates sheet (list of contr to offset exp in table A (est exp))
Note on L40: worsfoldv: From table B estimates sheet (list of contr to offset exp in table A (est exp))

## HRA -approved
GUILDFORD B.C. - HOUSING INVESTMENT PROGRAMME 2023-24 to 2028-29: HRA APPROVED PROGRAMME
| Project | 2022-23 | Project | 2023-24 | Carry | 2023-24 | Expenditure | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | Total
| Budget | Actual | Spend at | Estimate | Forward | Revised | as at | Projected | Estimate | Estimate | Estimate | Estimate | Estimate | Project
|  |  | 31-03-23 |  |  | Estimate | 03.01.24 | Outturn | [5 empty] | Exp
| £000 | £000 | £000 | £000 |  | £000 | 0 | £000 | £000 | £000 | £000 | £000 | £000 | £000
Acquisition of Land & Buildings | 22900 | 4164.725 | 18382.406 | 4000 | 517.594 | 4517.594 | 2440.8109 | 4517.594 | 0 | 0 | 0 | 0 | 0 | 22900
New Build
Guildford Park | 6575 | 1765.503 | 5366.047 | 1084 | 124.953 | 1208.953 | 243.7324 | 744.827 | 464.126 | 0 | 0 | 0 | 0 | 6575
Bright Hill (no longer reqd) | 500 | 49.561 | 66.641 | 423 | 10.359 | 433.359 | 0.06988 | 0.359 | 0 | 0 | 0 | 0 | 0 | 67
Foxburrows Redevelopment | 10657 | 0.058 | 0.058 | 9591 | 0 | 9591 | 0 | 0 | 9591 | 1066 |  |  |  | 10657.058
Shawfield Redevelopment | 300 |  | 3.716 | 296 | 0.284 | 296.284 | 0 | 0.284 | 296 | 0 |  |  |  | 300
Various small sites & feasibility/Site preparation | 1000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000
Pipeline projects: | 9425 |  | 6.592 | 3422 | 5700.006 | 9122.006 |  | 0 | 0 | 0 | 0 | 0 | 0 | 9122.278
Manor House Flats |  | 20.045 | 95.402 |  |  | 0 | 17.9868 | 74.099 | 59.345 | 1271.454 | 1688.323 | 292.455
Banders Rise |  | 4.788 | 27.782 |  |  | 0 | 2.6218 | 2.041 | 0 | 0
Station Road East |  | 4.061 | 27.077 |  |  | 0 | 6.2905 | 60.204 | 354.783 | 313.84 | 61.535
Dunmore Garden Land |  | 4.591 | 39.129 |  |  | 0 | 31.4188 | 72.912 | 445.031 | 61.242 | 50.52
Clover Road Garages |  | 10.753 | 56.696 |  |  | 0 | 7.12 | 101.475 | 1071.219 | 1587.793 | 272.211
Rapleys Field |  | 11.029 | 28.781 |  |  | 0 | 6.4723 | 89.793 | 728.768 | 1183.589 | 197.697
Georgelands 108 |  | 4.062 | 5.135 |  |  | 0 | 10.2643 | 71.855 | 358.534 | 45.539 | 35.955
27 Broomfield |  | 4.958 | 8.683 |  |  | 0 | 6.7896 | 58.596 | 325.185 | 45.427 | 36.007
17 Wharf Lane |  | 4.173 | 7.717 |  |  | 0 | 6.4597 | 56.694 | 311.592 | 43.655 | 34.371
|  |  |  | 18816 | 6353.196 | 25169.196 | 2780.0369 | 5850.733 | 15005.583 | 5618.539 | 2376.619 | 292.455 | 0
Development Projects | 7100 |  |  | 7100 |  | 7100 |  | 0 | 0 |  |  | 4748 |  | 7100
Schemes to promote Home-Ownership | [7 empty] | 0
Equity Share Re-purchases | annual | 0 | annual | 400 | 0 | 400 | 0 | 400 | 400 | 400 | 0 | 0 | 0 | annual
Major Repairs & Improvements |  |  |  | 20600 | 6736 | 27336 |  | 27336 | 0
Retentions & minor carry forwards | annual | 0 | annual |  |  |  | 0 | 0 | [5 empty] | annual
Modern Homes - Kitchens, Bathroons & Void refurb | annual | 6601.738 | annual |  |  |  | 13137.1779 | 0 | [5 empty] | annual
Doors and Windows | annual | 907.591 | annual |  |  |  | 1854.9346 | 0 | [5 empty] | annual
Structural/Roof | annual | 1055.641 | annual |  |  |  | 733.5968 | 0 | [5 empty] | annual
Energy efficiency: Central heating/Lighting | annual | 1947.692 | annual |  |  |  | 1099.5206 | 0 | [5 empty] | annual
General | annual | 9794.336 | annual |  |  |  | 5903.4582 | 0 | [5 empty] | annual
ICT - Housing Management System | 1900 |  |  | 950 |  | 950 |  | 950 | 950 | 0 |  |  |  | 1900
Grants
Cash Incentive Scheme | annual | 0 | annual | 0 | 0 | 0 | 0 | 0 | [5 empty] | annual
TOTAL APPROVED SCHEMES | 60357 | 26355.305 | 24121.862 | 47866 | 13089.196 | 60955.196 | 25508.7252 | 34536.733 | 16355.583 | 6018.539 | 2376.619 | 5040.455 | 0 | 59621.336

## HRA-prov
GUILDFORD B.C. - HOUSING INVESTMENT PROGRAMME 2023-24 to 2028-29: HRA PROVISIONAL PROGRAMME
| Project | 2022-23 | Project | 2023-24 | Carry | 2023-24 | 2023-24 |  | 2024-25 |  | 2025-26 |  | 2026-27 |  | 2027-28 |  | 2028-29 |  | Total
| Budget | Actual | Spend at | Estimate | Forward | Revised | Projected |  | Estimate |  | Estimate |  | Estimate |  | Estimate |  | Estimate |  | Project
|  |  | 31-03-23 |  |  | Estimate | Outturn | [11 empty] | Exp
| £000 | £000 | £000 | £000 |  |  | £000 |  | £000 |  | £000 |  | £000 |  | £000 |  | £000 |  | £000
New Build
Guildford Park | 39125 | 0 | 1224.776 | 1173 | 0 | 1173 | 0 |  | 3869.451 |  | 8472.459 |  | 6887.06 |  | 6007.289 |  | 12664 |  | 39125.035
Bright Hill Development | 16500 | 0 | 0 | 8680 | 0 | 8680 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Slyfield (25/26 £5m; 26/27 £44m) | 50000 | 0 | 0 | 0 | 1000 | 1000 | 0 |  | 0 |  | 5000 |  | 44000 |  | 0 |  | 0 |  | 49000
Foxburrows Redevelopment | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Shawfield Redevelopment | 3000 | 0 | 0 | 500 | 0 | 500 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | 10353 |  | 11353 | 0 | 0 | 3869.451 | 0 | 13472.459 | 0 | 50887.06 | 0 | 6007.289 | 0 | 12664 | 0 | 88125.035
Major Repairs & Improvements
Major Repairs & Improvements | annual |  | annual | 5500 | 0 | 5500 | 0 |  | 5500 |  | 5500 |  | 5500 |  | 5500 |  | 5500 |  | annual
Retentions & minor carry forwards | annual |  | annual | [15 empty] | annual
Modern Homes: Kitchens and bathrooms | annual |  | annual | [15 empty] | annual
Doors and Windows | annual |  | annual | [15 empty] | annual
Structural | annual |  | annual | [15 empty] | annual
Energy efficiency: Central heating | annual |  | annual | [15 empty] | annual
General | annual |  | annual | [15 empty] | annual
Grants
Cash Incentive Scheme | annual |  | annual | 75 |  | 75 | 0 |  | 75 |  | 75 |  | 75 |  | 75 |  | 75 |  | annual
Total Expenditure to be financed | 108625 | 0 | 1224.776 | 15928 | 1000 | 16928 | 0 |  | 9444.451 |  | 19047.459 |  | 56462.06 |  | 11582.289 |  | 18239 |  | 88125.035

## HRA-Resources
GUILDFORD B.C. - HOUSING INVESTMENT PROGRAMME 2023-24 to 2028-29: HRA RESOURCES AND FUNDING STATEMENT
| 2022-23 | 2023-24 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29
| Actual | Estimate | Projected | Estimate | Estimate | Estimate | Estimate | Estimate
Outturn
| £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
EXPENDITURE
Approved programme | 26355.305 | 47866 | 34536.733 | 16355.583 | 6018.539 | 2376.619 | 5040.455 | 0
Provisional programme | 0 | 15928 | 0 | 9444.451 | 19047.459 | 56462.06 | 11582.289 | 18239
Total Expenditure | 26355.305 | 63794 | 34536.733 | 25800.034 | 25065.998 | 58838.679 | 16622.744 | 18239
FINANCING OF PROGRAMME
Capital Receipts | 694.86 | 400 | 400 | 400 | 400 | 0 | 0 | 0
1-4-1 recepits | 2372.0915 | 8094 | 2340.2932 | 7550.0136 | 7636.3992 | 21305.4716 | 4302.1156 | 5065.6
Contribution from Housing Revenue a/c (re cash incentives) | 0 | 75 | 0 | 75 | 75 | 75 | 75 | 75
Future Capital Programme reserve | 10719.4109 | 27014 | 16334.281 | 950 | 0 | 0 | 0 | 0
Major Repairs Reserve | 9587.5857 | 6450 | 11951.719 | 5500 | 5500 | 5500 | 5500 | 5500
New Build Reserve | 2981.3541 | 21761 | 3510.4398 | 11325.0204 | 11454.5988 | 31958.2074 | 6453.1734 | 7598.4
Grants and Contributions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Financing (= Total Expenditure) | 26355.3022 | 63794 | 34536.733 | 25800.034 | 25065.998 | 58838.679 | 16330.289 | 18239
RESERVES - BALANCES | 2022-23 | 2023-24 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29
| Actual | Estimate | Projected | Estimate | Estimate | Estimate | Estimate | Estimate
Outturn
| £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
Reserve for Future Capital Programme (U01035)
Balance b/f | 40828.532 | 31782 | 32609.121 | 18774.84 | 20324.84 | 22824.84 | 25324.84 | 27824.84
Contribution in year | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500
Used in year | -10719.411 | -27014 | -16334.281 | -950 | 0 | 0 | 0
Balance c/f | 32609.121 | 7268 | 18774.84 | 20324.84 | 22824.84 | 25324.84 | 27824.84 | 30324.84
Major Repairs Reserve (U01036)
Balance b/f | 9587.586 | 1210 | 6426.719 | 0 | 0 | 0 | 0 | 0
Contribution in year | 17146.129 | 5525 | 5525 | 5500 | 5500 | 5500 | 5500 | 5500
Used in Year | -20306.996 | -6450 | -11951.719 | -5500 | -5500 | -5500 | -5500 | -5500
Balance c/f | 6426.719 | 285 | 0 | 0 | 0 | 0 | 0 | 0
New Build Reserve (U01069)
Balance b/f | 63788.072 | 66261 | 66068.128 | 69631.6882 | 66689.6678 | 63785.729 | 40549.1948 | 42992.1281
Contribution in year | 5261.411 | 8383 | 7074 | 8383 | 8550.66 | 8721.6732 | 8896.1067 | 9074.0288
Used in Year | -2981.355 | -21761 | -3510.4398 | -11325.0204 | -11454.5988 | -31958.2074 | -6453.1734 | -7598.4
Balance c/f | 66068.128 | 52882 | 69631.6882 | 66689.6678 | 63785.729 | 40549.1948 | 42992.1281 | 44467.7569
Usable Capital Receipts: 1-4-1 receipts (T01011)
Balance b/f | 5226.483 | 5630 | 6182.605 | 7638.4986 | 2870.4454 | -1871.7457 | -20193.9076 | -21421.3963
Contribution in year | 3935.766 | 2876 | 3796.1868 | 2781.9604 | 2894.2081 | 2983.3097 | 3074.6269 | 3168.2148
Repayment in year | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Used in Year | -2979.644 | -8094 | -2340.2932 | -7550.0136 | -7636.3992 | -21305.4716 | -4302.1156 | -5065.6
Balance c/f | 6182.605 | 413 | 7638.4986 | 2870.4454 | -1871.7457 | -20193.9076 | -21421.3963 | -23318.7815
Note: a contribution to this reserve is dependent on the number of RTB sales in the year determined in the HRA self financing model. There are many variables to the calculation of the
1:4:1 contribution. As an estimate, I have used a model provided by Sector which is based on our assumption of RTB sales
Usable Capital Receipts - HRA Debt Repayment (T01010)
Balance b/f | 5279.574 | 6123 | 5858.89 | 6004.0715 | 6856.114 | 7741.375 | 8654.5678 | 9596.4488
Contribution in year | 579.316 | 722 | 145.1815 | 852.0425 | 885.261 | 913.1928 | 941.881 | 971.3449
Used in Year | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Balance c/f | 5858.89 | 6845 | 6004.0715 | 6856.114 | 7741.375 | 8654.5678 | 9596.4488 | 10567.7938
Note: each RTB sale generates a contribution to this reserve toward debt repayment determined in the HRA self financing model. A small number of sales are anticipated each year.
Usable Capital Receipts - pre 2013-14 (T01008)
Balance b/f | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contribution in year | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Used in Year (HRA = above) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Used in Year (GF Housing Co) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Used in Year (GF Housing - DFG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Balance c/f | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note: Can only be used for HRA capital expenditure, affordable housing and regeneration schemes as set by GBC policy
Usable Capital Receipts - post 2013-14 (T01012)
Balance b/f | 50.099 | 348 | -2e-05 | 300.7445 | 312.4965 | 324.286 | 336.1433 | 351.0993
Contribution in year | 644.761 | 301 | 300.7445 | 303.752 | 306.7895 | 309.8574 | 312.956 | 316.0855
Used in Year (HRA = above) | -694.86 | -100 | 0 | -220 | -220 | -220 | -220 | -78
Used in Year (GF Housing) | 0 | -189 | 0 | -72 | -75 | -78 | -78 | 0
Balance c/f | -2e-05 | 360 | 300.7445 | 312.4965 | 324.286 | 336.1433 | 351.0993 | 589.1848
Note: Can only be used for HRA capital expenditure, affordable housing and regeneration schemes as set by the Government